## Slide 1: XBID Overview
SWE IG Meeting
Paris, CRE
07.04.2014
Supported by

## Slide 2: Agenda
Project structure and interfaces
High level overview of current project status
XBID Joint project approach
High level PX project plan with DBAG
Early Start Agreement Step 1 – Overview & Timeline
Update on Shipping and Nomination
Summary and discussion

## Slide 3: Project structure and interfaces

## Slide 4: High level overview of current status (1)
    Cost recovery
      Letter of Cost Comfort has been received by PXs and TSO’s; it confirms 100% recovery of allowed costs subject to conditions. ‘NWE+’ TSOs have confirmed their agreement to the ‘NWE+’ PX’s.
    PXs’ Cooperation Agreement (PCA)
      Agreement has been reached between the PX’s to enable the Agreement with DBAG to be signed
    PX/TSO Joint Project
        Project Management Core Team established – program management coordination reflecting the Joint Project, PXs and TSOs. Core team meets weekly and reviews high level issues and resolution.
        Joint Steering Group, Co-ordination Team and 3 Task Forces (Legal, IT and Pre & Post Coupling) are in place with members from both PX’s and TSO’s present in each

## Slide 5: High level overview of current status (2)
    Delivery of Early Start Agreement (ESA) Step 1
      Progress has been made to complete this phase which defines the content of the solution to be developed
        Investment in this phase provides the foundation for all parties
      We are tackling challenging issues which are essential for the long term success of the project but which are taking time to resolve. These include:
        Equal Treatment
        Performance
        Testing
      We have a plan to complete ESA Step 1 by Easter which remains a challenge. We have an approach to close open issues if any remain at this point
    Initial ideas have been shared on developing the future model for shipping and nomination

## Slide 6: XBID Joint project approach
Coordinate Design and Development of Interim Solution
(monitoring and directing)
Project under ESA
Local /Regional Implementation Projects
Follow-up/coordinate implementation of
Interim Solution
Roadmap interim Solution
LIPs framework conditions satisfied
XBID Interim Solution delivered and accepted
Project under contract
D&D contract
Business Blueprint
Common framework for pre- and postcoupling
Design Local /regional Implementation projects (LIPs)
Roadmap info from LIPs

## Slide 7: High level PX project plan with DBAG
ESA Signature
6 weeks
4 months
1 year (depends on the project planning in ESA Step 1)
ESA Step 1
ESA Step 2
Project under ESA
Project under Contract
Project Planning (for ESA Step 2 onwards)
Quality planning
Design and Development
Business Blueprint
D&D Contract Negotiation
Maintenance Contract Negotiation
Development and infrastructure
FAT & IAT
UAT
Activities

## Slide 8: Early Start Agreement Step 1 - Overview
Delivery 3 Batch 2
Delivery Prior Step 1
Delivery 3 Batch 1
Delivery 1
Description of ESA deliverables:
Specification of basic principles on project documentation (e.g. documentation management)
Project management principles for handling of issues, changes, risks and communication
Project terms and principles of equal treatment
Project and quality planning, definition of the work products, test strategy
Notes: Audience: TSOs, NRAs, ACER, ….

## Slide 9: Early Start Agreement Step 1 - Timeline
ESA validation by Vendor board
ESA ready to be signed
PCA - SC approval of 2nd step assessment
ESA signed
ESA validation by PX boards
Comfort Letter issued
PCA ready to be signed
PCA signed
ESA Step 1
24.1.14
- Completed
- Date
Delivery 3 Batch 2
Delivery Prior Step 1
Delivery 3 Batch 1
Delivery 1
3.2.14
13.2.14
15.04.14
Decision on ESA Step 2
Stakeholder Review &Confirmation
Lessons Learnt Review
Mobilisation ESA Step 2
17.1.2014
- Delay with significant impact
Beginning
May14
Commence ESA Step 2
02.04.14
Notes: Audience: TSOs, NRAs, ACER, ….

## Slide 10: Update on Shipping and Nomination
An Intraday continuous capacity allocation market imposes far more challenging requirements to the shipping and nomination process than for the Day Ahead (DA) market
  Cross-border allocation settlement processes must be concluded within a short period before real time to facilitate the short gate closure times
  This requires high robustness of the TSO operational processes to conclude the cross-border capacity allocation settlement into the required schedules (e.g. for controlled devices: load frequency controllers, phase shifters & DC cable flows)
The two options on cross-border nomination are being evaluated
  1) Border to border and 2) Hub to hub
TSO’s perspective: The existing DA solutions for shipping and nomination will have limited geographic scope for the scale of implementation required to facilitate an orderly Intraday market on a pan-European scale. A hub to hub approach may be necessary.
4 aggregation options of functions for shipping and nomination have been identified for the above 2 options, which gives a total of 8 potential options to be evaluated
Joint assessment of a potential centralised solution and the governance implications needs to completed. High level scoring on quality, costs, implementation time and future proofing has started at a working level and will be progressed over the coming weeks. There are resource constraints at present due to the priority on completing ESA Step 1
Full resolution of this topic is needed before start of LIPs. The immediate need, so as to ensure that the blueprint phase is not delayed, is to look at functional implications, if any, with an impact on the XBID system.
Notes: Limitation of geographical scope

## Slide 11: Summary and discussion
  Whilst progress has been made with ESA Step 1 the process and complexity, together with challenges of reaching alignment have been significant. All parties are striving to resolve key issues rather than allowing these to cause subsequent project delays
  These key issues involve Equal Treatment, Performance and Testing
  The extension of ESA Step 1 has involved additional cost
  All parties are targetting completion of ESA Step 1 by Easter which remains a challenge. There is a plan to allow a short period to ensure full agreement to Step 1 (including as necessary with NRAs) before starting Step 2. This also allows for a “lessons learnt project review” to improve processes
  It is expected that a period of around 12-13 months will be required to deliver the XBID solution. It is essential that aspects such as Integration Testing are included to ensure robust implementation.
  Agreeing the future model for shipping and nominations is key. The different options being considered have varying impacts on implementation timescales, the costs of the solution and scalability.
  Development of the Local Implementation Projects (LIPs) and roadmap is to be undertaken once the Business Blueprint phase is completed. Where possible and subject to confirmation LIP implementation will be run in parallel with the XBID solution project