## Slide 1
Deliverable I.4 Cross-border balancing model among TSOs
-BALIT project-
(7th SG SWE, Lisbon, December 3rd 2013)

## Slide 2
  Background
  April 2013:
  Signature of Memorandum of Understanding (MoU) between the parties (RTE, REN and REE) for the implementation of this project
  8th July 2013: 12th IG SWE meeting:
  information on the project to ERI SWE RCC.
  Foreseen go-live: February 2014
  Monthly report to NRAs:
  Monthly reports to each NRA about the progress on the BALIT project (Dashboard and regulation and legal overview documents)

## Slide 3
  Status of the project (Q4 2013)
  Regulatory changes in the respective systems
  Spain:
    Modification of M.O. 4112/2005 (pending)
    October 2013: Consultation on Operational Procedures was launched by REE
    Beginning December 2013: Submission of Operational Procedures to Spanish Ministry.
  Portugal:
    Modification of the “Manual de Procedimentos da Gestão Global do Sistema”
    Submission to ERSE: December 2013
  France: No regulatory changes
Contractual agreements
  Signature of RTE-REN-REE Memorandum of Understanding (MoU) (done – April 2013)
  Service Provision Agreement (SPA) for the usage of BALIT (REN-RTE and REE-RTE) (ready for signature)
  Cross Border Balancing (CBB) Agreements between RTE-REE and REN-REE (not closed yet)
  IT issues
  BALIT Implementation Guide (REN, RTE, REE): To be attached to the SPA (finished)
  Other impacted Implementation Guides (ECAN and SO-SO matching) (finished)
  IT developments (finalization phase)
  IT tests (in progress)
    Beginning Nov - Beginning Dec 2013: First individual IT tests with BALIT platform
    Joint tests with BALIT platform planned to start by mid January 2014

## Slide 4
Project Status
April
IT Specs
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
IT developments
Individual IT BALIT Testing
Joint Testing
Regulatory evolutions
Public consultation(s)
Regulatory approval(s)
Go Live
Today
  Implementation: February 2014 (subject to previous approval of required regulatory changes)
Road Map (November 2013)

## Slide 5
BALIT project
-Additional details-
(7th SG SWE, Lisbon, December 3rd 2013)

## Slide 6
  Design of Cross-Border Balancing Services: BALIT platform
  Goal and scope:
    Two bilateral mechanisms (IFE and IPE)
    Cross Border Balancing mechanisms will allow TSOs to:
      offer their surplus of balancing reserves to the other TSO
      take balancing resources when needed and economically interesting from other TSOs
  Design basis:
    Common IT Platform for the exchange of balancing services
      RTE: Service provider
      Platform: Already in use between FR-UK since 2010
    Balancing product:
      50 MW block
      Activation time: 30 min
      Firm during 1hour
    Common timetables
      Hourly process

## Slide 7
  Methodology
Based on exchange of balancing energy exceeding internal reserve margins required in the respective systems
The methodology for offering and activating cross border balancing bids (volume and price) will be transparent
This project is considered as an important first step in the establishment of cross border balancing mechanisms in the SWE that will enable the TSOs of the SWE region to gain experience towards the future implementation of:
  Regional models (multilateral TSO models allowing unshared bids), and
  Long Term Target Model (Submission of all the balancing bids to the cross border balancing platform, which will correspond to further integration of balancing markets), in line with the Framework Guidelines and Network Code on Electricity Balancing