## Slide 1: SWE Day- Ahead market coupling
25 February 2014
Implementation Group meeting – Madrid
Draft

## Slide 2: Price caps and bid caps
  There are no Market results price caps in MIBEL. What exists in MIBEL are limits on bid prices (currently 0-180), which do not imply limits to the Market results prices.
  Therefore, any bids with higher and lower prices from other countries can be matched in PCR, and any resulting Market price is accepted in MIBEL (including negative prices and/or prices higher than 180).
  Price caps and caps on the bids on EPEX’s side were agreed in the framework of the NWE Project based on studies and recommendations from Market Parties
 | Market results Price cap | Bid cap
OMIE | Not applicable | 0/+180
EPEX | -500/+3000 | -500/+3000

## Slide 3: Fallback for SWE full coupling
In case decoupling occurs, the MIBEL Day Ahead market will run independent from the rest of the Day Ahead Markets.
In order to avoid any delay in the full coupling go-live date, last 3rd December the SWE NRAs decided to follow a two steps approach:
“The IG agreed that market coupling is the highest priority of the SWE region in the short term and any potential delay should be avoided. In this context, NRAs support intraday allocation as fallback mechanism, only as a transitory solution, in order to avoid any delay in the launch of this project.”
  The full coupling is foreseen to be launched in May with Intraday allocation as a fallback transitory solution.
  Works for the implementation of Shadow auctions are being carried out in parallel. This implementation will require:
    Regulatory changes
      New Allocation Rules at FR-ES interconnection
      Updates on Spanish Operational Procedures
      Adaptation of High Level Regulation
    Contractual updates
      CASC Service Level Agreement
      RTE-REE Cooperation Agreement
    IT developments and testing
      Updates and developments of new information exchanges
    Communication plan towards Stakeholders
    Regulatory comfort for needed regulatory updates and cost recovery, when needed
Regarding the allocation of Day Ahead cross zonal capacity at the PT-ES interconnection, existing MIBEL market mechanisms will apply.
FR-ES Interconnection
PT-ES Interconnection
Possibility to perform it simultaneously with the future extension of HAR to FR-ES interconnection

## Slide 4: High level planning – SWE Full coupling
 |  | Dec | Jan | Feb | March | April | May | June | July | August
Operational activities |  |  |  |  |  |  |  |  |  | 
Testing activities |  |  |  |  |  |  |  |  |  | 
Regulatory evolutions |  |  |  |  |  |  |  |  |  | 
2014
Operators training
MPs training
Procedures refinement
Signed
SWE contracts
Version
18/02/2014
Integration testing
NWE test for SWE Start up solution
Succesfull testing
Auction rules evolution
Regulatory approval
French I/E Rules
NWE / SWE tests
Go live
Prep
Today
Public consultation(s)
NWE/SWE Task Force
Simulation tests
Member tests
SWE Full Coupling Go live window
Integration testing
Regulatory approval
IFE rules
2013
High level Spanish regulation approval