## Slide 1: SWE Day-ahead market coupling (Pre- and Post-Coupling project) Lisbon, 3rd December 2013 10th Implementation Group meeting

## Slide 2: Agenda
SWE-NWE coupling implementation: two steps approach
Achieved, ongoing and pending milestones
Fallback for SWE full coupling
1
3
2
Project planning
4

## Slide 3: SWE-NWE coupling implementation: two steps approach
SWE and NWE regions have decided on the common synchronized Go live of the operations of NWE and SWE Day Ahead markets in February 2014 following a two steps approach.
From the Start-up phase (February 2014, simultaneously with NWE):
  In a first step, called the “start-up solution”, it is envisaged set up common synchronized operations of the day-ahead markets in the NWE and SWE regions, using the same PCR Matcher-Broker (PMB) systems and operational procedures.
  During this step, the daily explicit auction at the France-Spain border will be maintained and consequently zero cross-zonal capacity values will be used for that border in the matching algorithm for implicit allocation.
  All procedures for the Startup phase (SWE, NWE and PCR) will be applied by all the involved parties
  One of the main changes needed for this phase was the change of MIBEL DA Market GCT to 12h and has been achieved 15th October.
From the Full coupling Go-live:
  France-Spain ATC will be allocated implicitly through the run of Day Ahead Market Coupling algorithm (i.e.: the existing daily explicit auctions will disappear).
  All procedures for the Full coupling (SWE, NWE and PCR) will be applied by all the involved parties.
  The Full coupling Go-live date (foreseen for April 2014) will be defined once the needed IT developments and regulatory evolutions have been performed
 | Start-up phase | Full coupling
FR-ES Capacity value offered to DA Market Coupling | 0 | Agreed ATC between RTE and REE
FR-ES DA Capacity Allocation | Explicit | Implicit

## Slide 4: Agenda
SWE-NWE coupling implementation: two steps approach
Achieved, ongoing and pending milestones
Fallback for SWE full coupling
1
3
2
Project planning
4

## Slide 5: Achieved, ongoing and pending milestones
Technical milestones
  Change of MIBEL Day Ahead Market Gate Closure Time to 12h CET achieved (15th October 2013)
  Integration and simulation tests ongoing
  Member tests ongoing
  Development of some specific IT exchanges for post-coupling activities ongoing
  Stop of FR-ES daily explicit auctions ongoing
Regulatory milestones
  MIBEL regulatory framework for the change of GCT to 12h achieved (9th August in ES and 1st October in PT)
  Regulatory framework for the use of Euphemia algorithm both in the MIBEL and French DA Market ongoing
  Update on FR-ES capacity allocation rules ongoing
  Update on French Import/Export Rules ongoing
  Update on Spanish high level Regulation ongoing
  Update on Spanish Operational Procedures ongoing
Contractual milestones
  Update on Agreement between REN and OMIE achieved
  OMIE-EPEX agreements ongoing
  RTE-EPEX post-coupling contractual agreements ongoing
  SWE Day Ahead Operational Agreement achieved
  Future European Day Ahead Operational Agreement ongoing
Start-up
Full coupling
X
X
X
X
X
X
X
X
X
X
X
X
X
X
X
X
X
X
X
X
X

## Slide 6: Agenda
SWE-NWE coupling implementation: two steps approach
Achieved, ongoing and pending milestones
Fallback for SWE full coupling
1
3
2
Project planning
4

## Slide 7: Fallback for SWE full coupling
In case decoupling occurs, the MIBEL Day Ahead market will run independent from the rest of the Day Ahead Markets. Regarding the allocation of cross zonal capacity at the FR-ES interconnection, two possible solutions for decoupling situations are being analyzed:
Intraday allocation
  The FR-ES ATC would be allocated through the first of the existing FR-ES intraday auctions covering the 24 hours of day D
  This solution is already in place for cases where current daily explicit auction is cancelled in FR-ES border
  This solution does not need any significant new development, specific tests or update on existing systems and facilities
  This solution can be implemented from the first day of application of full coupling phase and could also be a backup solution for Shadow Auctions when applicable
  Although this solution does not provide with the most efficient allocation of capacity it must be noted that it will only be applied in very exceptional situations
Shadow auctions
  This solution would allow using cross zonal capacity in the Day Ahead Market, through daily explicit auctions
  During the 12th SWE IG meeting the RCC accepted that Shadow Auctions may be necessary for the FR-ES border but only needed during the full coupling phase
  Shadow auctions will be implemented as fallback only in a second step
  This solution has an associated cost and may require, prior to its implementation, NRAs comfort for regulatory changes and costs recovery
  This solution may imply a more efficient allocation of capacity but may also require delays in the subsequent processes of generation scheduling, which can be managed by OMIE and REE
Regarding the allocation of Day Ahead cross zonal capacity at the PT-ES interconnection, existing MIBEL market mechanisms will apply.

## Slide 8: Agenda
Project planning
4
SWE-NWE coupling implementation: two steps approach
Achieved, ongoing and pending milestones
1
2
Fallback for SWE full coupling
3

## Slide 9: High level planning Start up solution
 |  | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb
Operational activities |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IT developments |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Testing activities |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Regulatory evolutions |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NWE/SWE Task Force
2013
2014
NWE Go live window
Design phase
Implementation preparation
Project implementation plan
Design approval
Operators training
Contractual framework drafting
MPs training
IT Specifications
Master test plan definition
Master test plan
Integration testing
Member
testing
Coordination with NWE
Participating in PCR/NWE testing
Pre-Coupling IT developments
Local regulation evolutions/changes for 12.00 GCT
MIBEL NRAs
Public consultation
Regulatory approval(s)
* If needed
Local testing
Post-Coupling IT developments
Decision on Start up solution (simultaneous Go live with NWE)
Simulation tests
Entrance testing
Today
Market rules evolutions/changes (algorithm…)
MIBEL NRAs Public consultation
Version
18/11/2013
Decision on NWE and SWE Start up solution Go live date

## Slide 10: High level planning – SWE Full coupling
 |  | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | April | May
Operational activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IT developments |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Testing activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Regulatory evolutions |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Contracts drafting
2013
2014
NWE Rollback period with SWE Start-up solution
Project implementation plan
Signature of amendment to Cooperation Agreement
Design approval
Implementation preparation
Operators training
MPs training
Procedures refinement
Signed contracts
TSO’s IT developments
TSO’s IT specifications
IT ready for testing
PX’s IT developments
IT ready for testing
Version
28/11/2013
Design finalization
Master test plan
Master test plan definition
Local testing, RTE developments
Integration testing
Coordination with NWE testing activities for SWE Start up solution
Succesfull testing
Local regulation changes
Auction rules evolution
Regulatory approval(s)
Pre- Integration testing
NWE / SWE tests
Go live
Pre.
Today
Public consultation(s)
Public consultation(s)
Contracts finalization
NWE/SWE Task Force
Decision on Start up solution (simultaneous Go live with NWE)
Test Scripts definition
Simulation tests
Member tests
Approval of the SWE DAOA
SWE Full Coupling Go live window