## Slide 1
22th November 2019
52st IG meeting

## Slide 2
2.1. Follow-up of infrastructures developments

## Slide 3: 2.1 TYNDP 2020 & 4th PCI list 2019
*
Regional needs identification
Public consultation
NRAs consultation
Methodology drafting and publication
Technical Decision making body
ACER opinion
High Level Decision making body
Draft final 4th PCI list
Project submission
Practical Implementation Document (PID)
Project collection
System needs assessment
Project assessment CBA
PS-CBA Fiches
Draft TYNDP report
Final TYNDP report
Nov 18 - Mar 19
Nov - Dec 18
Feb - May 19
Mar- Apr 19
Mar - Jun 19
5th Jul 19
Jul – Sept 19
Mid-Oct 19
Oct 19
ENTSOs joint scenario development
& Scenario report
Spring 18 - Nov 19
May 19
May - Aug 19
Jan 20– March 20
Oct/Nov 19 – Mar 20
Apr 20
Public consul.
Jun – Jul 20
4th PCI list
TYNDP 2020
ENTOSG & EC´s milestones
Enagas´ milestones
Final report/list
Final 4th PCI list
Jan / Feb 20
Q2/Q3 20
  Infrastructure Report & Maps
  System Assessment Report
  Gas Quality Outlook
  Annexes

## Slide 4: 2.1 Focus on TYNDP 2020

## Slide 5: 2.1 PCI selection process
Common Decision of CRE and CNMC concerning the STEP
22nd Jan 19
STEP
Investment Request – ACER conclusion
22nd Jun 19
The final PCI assessment methodology was published by the EC
27th Jun 19
Technical Decision making body
Draft PCI list
ACER Opinion on the draft PCI list
30th Sept 19
5th Jul 19
31st Oct 19
Final PCI list publication (OJEU)
Jan/Feb 20
HLG
Tbc

## Slide 6
2.2. Report on the use of VIP infrastructures October 16- Sept19: progress and work calendar

## Slide 7: 2.2. Report on the use of VIP infrastructures October 16- Sept19: progress and work calendar
OCT 19
SEPT 19
NOV 19
DEC 19
JAN 20
FEB 20
MAR 20
Intermediate Report (report with Oct16-Jun19 data)
Final Report (report with Oct16-Sept19 data)
1st draft of the report
Completing and checking the 1st draft
2nd draft of the report (with Jun19 -Sept19 data)
Curent status:
Working on the first draft

## Slide 8
3.2 Follow-up gas prices

## Slide 9: 3.2 Follow-up gas prices
Day-ahead prices France, Spain and The Netherlands
Capacity utilization VIP Pirineos 1st Nov – 11th Nov 17-18 vs 18-19

## Slide 10: 3.2 Follow-up gas prices
Day-ahead prices France, Spain and The Netherlands

## Slide 11
Thank you for your attention!