## Slide 1: CAM: TIGF’s IT developments Roadmap
SGRI 23rd IG Meeting
19 June 2013

## Slide 2: TIGF adhesion to PRISMA
On 5 June 2013 TIGF sent to PRISMA a Letter of intent for the adhesion to the platform as from 1st January 2014
TIGF intents to join PRISMA as user and shareholder
TIGF is already working on the IT specifications and developments to connect the IT systems to PRISMA
TIGF has already launched internal IT developments to adapt existing internal IT systems to CAM NC provisions

## Slide 3: TIGF roadmap for IT Implementation of CAM NC
2013
2014
2015
LOI for adhesion to PRISMA
March
Platform adhesion decision
Detailed spec. and developments
Release
TEST environm.
Release
PROD environm
Full connection
Within-day products auctions
Phase 2 –
Within day products auctions
Connexion to PRISMA
Oct
Jan
Dec
June
March
June
Oct
Oct
TIGF internal IT systems developments
IT Specifications / developments
New capacity products
Capacity calculation
Auctions capacity offer building
Auctions results treatment
Publication of auction results
Invoicing
Single nominations and matching process (for bundled products)
Secondary market
Release
TEST environm
Testing
TEST environment
Release
TEST
Release
PROD
Testing
TEST environm
1st Annual Yearly products auction
1stAnnual Quarterly products auction
1st rolling Day-ahead product auction
1st rolling monthly product auction
IT Specifications / developments for Within-day auctions
Release
PROD environm
Release TEST/
PROD environm
IT Specifications / developments for
Day Ahead auctions
Jan
Testing
TEST environment
Jan
Creation of the VIP SP/FR

## Slide 4: TIGF roadmap for IT Implementation of CAM NC
Summary of key milestones:
LOI for adhesion to PRISMA : 5th June 2013
Full connexion to PRISMA: 1st January 2014
Creation of the VIP SP/FR: January 2014
1st annual Yearly auctions: 3rd March 2014
1st annual Quarterly auctions: 2nd June 2014
1st rolling Monthly auctions: 15th September 2014
1st rolling Day-Ahead auctions: 30th September 2014
1st Within-Day auctions: 1st October 2015

## Slide 5
Thank you for your attention