## Slide 1: NWE Day-ahead price coupling project Cost Issue
2nd IG Meeting
26 October
APX ENDEX

## Slide 2: Type and estimated amount of costs
Preliminary estimates of combined PX costs have been produced by APX ENDEX
  Based on NWE go live early 2013 using full PCR solution
  To be reviewed with TSOs on Friday 28th October
  €10mil estimated cost, including contingency
Key assumptions
  NWE PXs incur 60% of PCR common costs plus their own costs supporting PCR
  APX ENDEX estimated own costs are representative of other PXs
  Limited change to existing pre and post coupling arrangements (including shipping) across NWE region
  Limited change to existing contractual/regulatory arrangements across NWE region
  Phasing
    PCR is completing design, and is entering implementation phase Q4/Q1
    NWE design expected to be completed Q1; implementation start Q2

## Slide 3: Main Cost Elements
Chart: 
PCR European Solution | 6.5
Local Implementation of PCR | 0.9
NWE End to End Technical Solution | 2.3
NWE Contractual Solution | 0.4
PCR European Solution (60% share of common costs plus individual NWE PX contributions)
Local implementation of PCR
NWE End-to-End Technical Solution
NWE Contractual Solution
Drafting, negotiation, modification of enduring agreements
TSO adapter software
Shipping solution software
Operational procedures design
Integration and procedural testing
Local hardware and communications infrastructure
Trading system interfaces
Algorithm development (c. 30%)
- starting point; prototype development
- procure industrial version
- build/test industrial algorithm
System development (c. 40%)
- design, specify systems
- procure system provider
- build/test systems
Joint PX contracts (c. 10%)
PCR project management, contingency (c. 20%)

## Slide 4: Timing of Cost Commitments
Chart: 
| Pre Q4 2011 | Q4 2011 | Q1 2012 | Q2 2012 | Q3 2012 | Q4 2012 | Q1 2013
PCR European solution - design | 1672 | 969
PCR European solution - implementation | 922 | 1251 | 1087 | 397 | 195
Local PCR implementation | 550 | 175 | 175 | 0
NWE technical - design | 150 | 180
NWE technical - implementation | 860 | 360 | 360 | 360
NWE contracts - design | 50 | 50
NWE contracts - implementation | 60.4249 | 80 | 90 | 80

## Slide 5: Cost Sharing - PCR
PCR Common Costs
  Jointly managed/procured costs (e.g., project manager, workstream leaders, procurement manager, algorithm developer, system contractors, specific tasks)
  Shared equally between 5 lead PCR exchanges (in effect, 60% incurred by NWE PXs)
PCR Individual PX Costs
  PX costs incurred supporting PCR European solution deliverables
  Not shared between PXs
PCR Local PCR Implementation Costs
  Costs incurred by each PC installing PCR systems and interfaces to local trading systems
  Not shared between PXs
New parties joining PCR
  PCR open to new PXs: fair share of prior PCR investment (could be linked to market size, and option to be full party or not)