## Slide 1: Brief status on key on-going PCR activities NWE Regulators IG Meeting 28 Mar 2012

## Slide 2: Status for the following “next steps” that was listed in the 1 Feb AESAG meeting
To start the NWE project in a proper way and to comply with the planning presented, the following steps (including some PCR steps) have to be tackled:
Design of NWE pre-coupling (ATC handling) and post-coupling (Shipping agent mechanism)  NWE TSOs; To be carried out until summer in TFs in the joint NWE PX-TSO Project
Clarification of the specification on Nordic flows calculation (for the algorithm) by end of January and Nordic functionalities for PMB//PCS during February  PXs; DONE
Clarification and agreement on NWE fallback procedures  Joint NWE PX-TSO ; On-going
Finalise PMB provider selection  PXs; AGREED in PCR, but Contracts remain to be finalized
Finalisation of the PCR agreements (including governance and other terms)  PCR PXs; PROGRESSED WELL LATELY, and target is to have ready for signing by end of April
Interim agreement if needed (including governance and other terms for use the system in the interim)  PXs; PENDING. Initial proposal circulated
Finalisation of the NWE APCA and the cost recovery mechanism  Joint NWE; IN PROGRESS, refer to separate reporting from meeting held between PXs and TSOs late 27 March
Start the NWE project organisation (i.e. appoint joint PMO)  Joint NWE. WELL UNDERWAY, a dedicated TF has provided a recommendation for a PMO and it is to be reviewed in JSC soon

## Slide 3: PCR: Status of PCR GOWG Activities & deliverables
  Finalization of the PCR co-operation and co-ownership agreements.
    Very good face to face meeting in Paris 22 and 23 March with substantial progress
    Aim for finalizing both agreements before end of April based on meetings as follows:
    Telco 28 March, face to face meeting 11 April and 18-19 April and Telco 24 April
  Status of the Annexes to the PCR agreements: ongoing
  Internal validation and signature process for signing PCR Co-Own and Co-Op.
    Clarification by each PX is underway, and Board approval pending for some PXs
  NDA for an Access to PTDF data from NWE TSOs for the PCR ALWG work.
    Will be finalized within week 13

## Slide 4: What is the PCR Matcher-Broker (PMB)?
PMB is a software which embeds the PCR Algorithm executable and communicates with PCR PXs Trade Systems, and as needed with TSO software
The PMB system can be installed in the needed operational sites of PXs
Since September 2011, PCR PXs have greatly simplified the original PCR concept while maintaining the decentralized PCR architecture and responsibilities
Under such simplified PCR architecture, on a given day, there are two sites which play a determinant role in the PCR operations, while respecting the acceptance of the results by all involved PXs :
  1 PCR Coordinator
  1 PCR Hot-Backup Coordinator
Other PXs can act as Operators which make calculations in shadow mode for acceptance purposes every day (=>decentralized responsibility)
  These equipments are needed anyway for all Operators in addition to the Coordinator and Hot Backup Coordinator in the extreme cases of partial decoupling

## Slide 5: PCR Procurement status for PCR Matcher-Broker (PMB)
Key status points for PCR SDWG work related to PMB
  PMB project continues progressing with all PXs involved ; is on schedule
  Weekly meeting held in PCR SDWG to clarify questions raised in PMB and advance in System Design Issues
  PMB Test Plan to be discussed in next weekly meeting
Activities towards the PMB supplier
  Analysis work with the supplier is currently based on funded LOI with 4 PCR PXs
  Development agreement with supplier being negotiated, signature of all PCR PXs of the development agreement planned for end of April

## Slide 6
ALWG: General Status of work with PCR Algorithm
Algorithm Requirements almost finalized, except:
  potential additional requirements from NWE TSOs
  finalization of curtailment rules
Capacity Allocation Requirements
  finalization with NWE TSOs monitoring group in progress
  Formal validation expected from NWE TSOs
Next steps
  assessing to what extent NWE TSOs requirements can be implemented under the NWE planning
  writing specifications for PCR Algorithm
R&D activities
  prototyping on Iberian features finished
  Prototyping Italian features progressing
Notes: 6